## Rohit Agrawal
Week # (From Date - End Date) | Total Actual Time (This Week Tasks) (# Hours) | Total Individual Work Time (# Hours) | Total Meeting Time (# Hours) | Task Breakdown 0 - Learning 1 - Requirement Analysis 2 - Design 3 - Implementation 4 - Test 5 - Communication/Management 6 - Unclassified | Task #0 Time (# Hours) | Task #1 Time (# Hours) | Task #2 Time (# Hours) | Task #3 Time (# Hours) | Task #4 Time (# Hours) | Task #5 Time (# Hours) | Task #6 Time (# Hours) | Estimated Tasks (Next Week) | Total Estimated Time (# Hours)
09/06/2017 - 09/12/2017 | 7 | 5 | 2 | 5 - Brainstorm potential project ideas with the group. 5 - Find out the strengths of each of the group members and decide a technology stack. 5 - Brainstorm the project and team name. 5 - Mutually decide a convinient meeting time. 0 - Read more about Spring and microservices. | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0, 1, 2, 3, 5 | 15
09/13/2017 - 09/19/2017 | 20 | 15 | 5 | 1 - Perform Requirement Analysis to understand the scope of the project and the essential features. 1 - Write a project description outline with the desirable features. 5 - Setup two different Slack channels for the general communications and the project progress updates. 5 - Setup GitHub repository and allocate roles by identifying the access levels for individual group members. 3 - Add a simple Readme file consisting of the project outline and desirable features to demonstrate GIT best practices like Branching Techniques, Commit/Squash Practices, Code Reviews, PR Merges etc. 5 - Discuss an agile methodology flavor Vanilla/Kanban and setup the JIRA Board [Taiga]. 5 - Identify and assign the various leadership roles to the group individuals in Taiga Board. 2 - Document the software installation guide for the complete technology stack including the static analysis tool and the continuous integration tool. 0 - Read about SpringBoot and the various dependency and build manager tools. | 2 | 3 | 2 | 1 | 0 | 7 | 0 | 0, 1, 2, 3, 4, 5 | 20
09/20/2017 - 09/27/2017 | 25 | 20 | 5 | "1 - Brainstormed detailed requirements and outline of the project with all the team members. 0 - Installed TeamCity, SonarQube, JDK 8, Eclipse & Plugins to setup Development Environment. 0 - Looked into the Chart Libraries like ECharts, C3, D3, NVD3, TauCharts. 0 - Read more about SOA, Microservices, Spring & SpringBoot. 0 - Looked into 3D Visualization Tools like DEX. 3 - Created PivotalTracker account and wrote UserStories along with Yash. 1,2 - Worked on main areas of SPPP along with Yash. 5 - Worked on the overall project architecture design. 5 - Documented GIT Branching strategy in detail with the branch prefixes and code reviews policies. 5 - Documented Definition of Done (DoD). 5 - Documneted Sprint lengths, story points, planning & scrum meeting times. 5 - Made smaller teams for iteration 0 and iteration 1 presentations with mutual consensus. 5 - Assigned stories and individual tasks for each team member for the upcoming sprint. 5 - Discussed the code review process with the Implementation Leader." | 4 | 2 | 3 | 2 | 0 | 9 | 0 | 0, 1, 2, 3, 4, 5 | 20

## Yashvardhan Nanavati
Week # (From Date - End Date) | Total Actual Time (This Week Tasks) (# Hours) | Total Individual Work Time (# Hours) | Total Meeting Time (# Hours) | Task Breakdown 0 - Learning 1 - Requirement Analysis 2 - Design 3 - Implementation 4 - Test 5 - Communication/Management 6 - Unclassified | Task #0 Time (# Hours) | Task #1 Time (# Hours) | Task #2 Time (# Hours) | Task #3 Time (# Hours) | Task #4 Time (# Hours) | Task #5 Time (# Hours) | Task #6 Time (# Hours) | Estimated Tasks (Next Week) | Total Estimated Time (# Hours)
09/06/2017 - 09/12/2017 | 8 | 6 | 2 | 0 - Getting a background about the services to be implemented 5 - Assist the team leader to decide on the technologies to be used and assign work to the respective leaders 5 - Coordinate with the team leader and members to setup a weekly meeting schedule 5 - Make a document for the steps to be followed while working with git on the project 5 - Discuss more about the specifics of the project and find a project name | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0, 1, 2, 3, 5 | 15
09/13/2017 - 09/19/2017 | 18 | 13 | 5 | 0 - Getting acquainted with the Taiga Board. 0 - Digging deeper into Kibana which is similar to our idea with lesser features. 1 - Participate in the requirement analysis of the project. 2 - Review the software installation guide for the complete technology stack. 2 - Figure out shortcomings of Kibana and research on the methods using which we can avoid those in our app. 5 - Discuss agile methodologies such as Vanilla/Kanban and help Rohit in setting up the JIRA Board [Taiga]. 5 - Coordinate with team members to assure that the work is on track. 5 - Review work of other team members and report to the team leader. | 4 | 3 | 4 | 0 | 0 | 6 | 0 | 0, 1, 2, 3, 4, 5 | 18
09/20/2017 - 09/27/2017 | 20 | 15 | 5 | 0 - Found and researched on an open-source project named DEX which inhibits 3D visualizations 0 - Learnt more about Spring and SpringBoot. 0 - Getting acquainted with Spring environment 0 - Setup the development environment 1 - Brainstormed requirements and outline of the project with all the team members 1,2 - Documented huge chunks of SPPP 3 - Setup the pivotal tracker and made user story cards with Rohit 5 - Conveyed the plan to all team members 5 - Co-ordinated with all the team members to setup an extra meeting for this week to finish up the requirements of iteration 0 5 - Made teams for presenting iteration 0 and iteration 1 with mutual consensus 5 - Discussed individual work for each team member and story points per sprint for them 5 - Discussed branching and configuration nuances such as hotfixes/features/bugs with the team 5 - Discussed the development model and project schedule with team leader | 4 | 2 | 3 | 2 | 0 | 8 | 0 | 0,1,2,3,4,5 | 20

## Anirvan Maiti
Week # (From Date - End Date) | Total Actual Time (This Week Tasks) (# Hours) | Total Individual Work Time (# Hours) | Total Meeting Time (# Hours) | Task Breakdown 0 - Learning 1 - Requirement Analysis 2 - Design 3 - Implementation 4 - Test 5 - Communication/Management 6 - Unclassified | Task #0 Time (# Hours) | Task #1 Time (# Hours) | Task #2 Time (# Hours) | Task #3 Time (# Hours) | Task #4 Time (# Hours) | Task #5 Time (# Hours) | Task #6 Time (# Hours) | Estimated Tasks (Next Week) | Total Estimated Time (# Hours)
09/06/2017 - 09/12/2017 | 10 | 8 | 2 | 5 - discussed the project ideas of the group 5 - discussed the pros and cons of each member sproject idea 5 - decided the team name 5 - decided a common meeting time and place as per every members convenience 0 - read more about the project and its use cases | 3 |  |  |  |  | 5 |  | 0, 1, 2, 3, 5 | 15
09/13/2017 - 09/19/2017 | 22 | 17 | 5 | 0 - researched about kibana. Its abilities and short comings 1 - discussed the scope of the projects and how to over come the short comings of kibana with the team 3 - set up the environment which will be used by all the members of the team during the entire duration of the project 5 - documented the software installation links and installation steps for the team members 0 - learnt more about agile methodology so that we can implement in the development process 0 - Read about Taiga board and how it works 5 - discussed the workflow skeleton for the project with all the team members 0 - researched about the testing process for the project and analyzed them 5 - discussed with the team about the requirements of the software and the fetures which can be added in it 0 - reviewed and read about the softwares and platforms to be used for the project | 5 | 2 | 2 | 1 | 0 | 7 |  | 0, 1, 2, 3, 4, 5 | 20
09/20/2017 - 09/27/2017 | 20 | 15 | 5 | 0 - researched and read more about the DEX visualization tool 0 - set up the environment along with the additional packages 0,1 - documented the SPPP along with other team members 5 - prepared for the iteration 0 presentation along with the team members 2 - Edited the iteration 0 presentation PPT 5 - mutually created smaller teams for alternate iteration presentations 1 - discussed the requirements of the project with the team members 5 - mutually discussed the strengths and weaknesses of the team members 0 - learnt and researched about other visualizations techniques 0 - learnt about the various testing processes which will/can be implemented in the project | 4 | 2 | 1 | 0 | 0 | 8 | 0 | 0,1,2,3,4,5 | 20

## Tianqi Xu
Week # (From Date - End Date) | Total Actual Time (This Week Tasks) (# Hours) | Total Individual Work Time (# Hours) | Total Meeting Time (# Hours) | Task Breakdown 0 - Learning 1 - Requirement Analysis 2 - Design 3 - Implementation 4 - Test 5 - Communication/Management 6 - Unclassified | Task #0 Time (# Hours) | Task #1 Time (# Hours) | Task #2 Time (# Hours) | Task #3 Time (# Hours) | Task #4 Time (# Hours) | Task #5 Time (# Hours) | Task #6 Time (# Hours) | Estimated Tasks (Next Week) | Total Estimated Time (# Hours)
09/06/2017 - 09/12/2017 | 0 | 0 | 0 | 6 - trying to register for the class. 0 - learning course material. | - | - | - | - | - | - | - | 0, 1, 2, 5 | 15
09/13/2017 - 09/19/2017 | 15 | 10 | 5 | 0 - read the papers about agile methodologies and no-silver-bullets. 0 - written assignments. 1 - determined group name. 1 - determined that we are going to use data visualization as our project topic. 1 - determined that we will use java, javascript and possibly matlab as our main language. 2 - finished the documentation for environment installation. 5 - Assigned role and different task for each group member. 5 - set a temporary group meeting time. 5 - get enrolled into pivot and github for future work | 7 | 1 | 1 | 0 | 0 | 7 | 0 | 0,1,2,3,5 | 20
09/20/2017 - 09/27/2017 | 17 | 12 | 5 | 0 - learnt the basic functionality of kibana and it's drawbacks that we want to improve 0 - recording the meeting minutes 0 - get to know eclipses and json more 0 - Setup thte environment 1 - Brainstormed requirements and assign more detailed tasks to group member 5 - Discussed more detailed plan for our 3 iterations: iteration 1 for parsing the data; iteration 2 for visualizing the parsed data; iteration 3 for design a wonderful UI and show the visualization in the UI 5 - Setup a fixed meeting time 5 - Determine the presentation cast | 4 | 2 | 3 | 0 | 0 | 8 | 0 | 0,1,2,3,4,5 | 20

## Wenjun Shen
Week # (From Date - End Date) | Total Actual Time (This Week Tasks) (# Hours) | Total Individual Work Time (# Hours) | Total Meeting Time (# Hours) | Task Breakdown 0 - Learning 1 - Requirement Analysis 2 - Design 3 - Implementation 4 - Test 5 - Communication/Management 6 - Unclassified | Task #0 Time (# Hours) | Task #1 Time (# Hours) | Task #2 Time (# Hours) | Task #3 Time (# Hours) | Task #4 Time (# Hours) | Task #5 Time (# Hours) | Task #6 Time (# Hours) | Estimated Tasks (Next Week) | Total Estimated Time (# Hours)
09/06/2017 - 09/12/2017 | [11 empty] | 0, 1, 2, 3, 5 | 15
09/13/2017 - 09/19/2017 | [11 empty] | 0, 1, 2, 3, 4, 5 | 20

## Aswin V.
Week # (From Date - End Date) | Total Actual Time (This Week Tasks) (# Hours) | Total Individual Work Time (# Hours) | Total Meeting Time (# Hours) | Task Breakdown 0 - Learning 1 - Requirement Analysis 2 - Design 3 - Implementation 4 - Test 5 - Communication/Management 6 - Unclassified | Task #0 Time (# Hours) | Task #1 Time (# Hours) | Task #2 Time (# Hours) | Task #3 Time (# Hours) | Task #4 Time (# Hours) | Task #5 Time (# Hours) | Task #6 Time (# Hours) | Estimated Tasks (Next Week) | Total Estimated Time (# Hours)
09/06/2017 - 09/12/2017 | 10 | 8 | 2 | 5 - Discussed about potential project ideas with the group. 5 - Assessed the strengths of each of the group members and decide a technology stack. 5 - Discussed the project and team name. 5 - Decided a convinient meeting time. 0 - Preparation on Spring and microservices. | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0, 1, 2, 3, 5 | 15
09/13/2017 - 09/19/2017 | 22 | 18 | 4 | 0 - researched about kibana. Its abilities and short comings 1 - discussed the scope of the projects and how to over come the short comings of kibana with the team 3 - set up the environment which will be used by all the members of the team during the entire duration of the project 5 - documented the software installation links and installation steps for the team members 0 - learnt more about agile methodology so that we can implement in the development process 0 - Read about Taiga board and how it works 5 - The workflow skeleton for the project 0 - Researched about the testing process 5 - discussed with the team about the requirements of the software and the fetures which can be added in it 0 - reviewed and read about the softwares and platforms to be used for the project | 5 | 2 | 2 | 2 | 0 | 6 |  | 0, 1, 2, 3, 4, 5 | 20
09/20/2017 - 09/27/2017 | 20 | 15 | 5 | 0 - researched and read more about the DEX visualization tool 0 - set up the environment along with the additional packages 0,1 - documented the SPPP along with other team members 5 - prepared for the iteration 0 presentation along with the team members 2 - Edited the iteration 0 presentation PPT 5 - mutually created smaller teams for alternate iteration presentations 1 - discussed the requirements of the project with the team members 5 - mutually discussed the strengths and weaknesses of the team members 0 - learnt and researched about other visualizations techniques 0 - learnt about the various testing processes which will/can be implemented in the project | 4 | 2 | 1 | 0 | 0 | 8 | 0 | 0,1,2,3,4,5 | 20