## Contribution
Student Name | Requirement Analysis (Pivotaltracker) | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (Github Code) | Testing (JUnit + Mockito / Manual Testing) | Configuration & Deployment | General Communication & Management
Rohit Agrawal | 1. Setup PivotalTracker 2. Created Iteration #0, #1 stories 3. Assigned story points by using poker cards 4. Successfully reviewed & accepted completed stories | 1. Actively participated in the requirement analysis & design discussions 2. Actively contributed in the initial draft 3. Created & added Project Logo 4. Proofread the document |  | 1. Planned and Created the Iteration #0 Presentation Presented Major Chunks [Iteration #0] 2. Planned and Created the Iteration #1 Presentation Presented Major Chunks [Iteration #1] 3. Planned and helped in creating the Iteration #1 Presentation [Iteration #2] 4. Planned and Created the Iteration #3 Presentation Presented Major Chunks [Iteration #3] | 1. Create Initial Skeleton [https://github.com/ukubuka/ukubuka-core] 2. Written ~85% Packages [UkubukaReader, UkubukaWriter, UkubukaExpressionEvaluator, UkubukaExtractor, UkubukaParser, UkubukaLoader] [82 Commits, ~9.1k LOC] [Full Report: https://github.com/ukubuka/ukubuka-core/graphs/contributors] 3. Create a new Project `ukubuka-scripts` for the Scripts. [Various Scripts Added: ~9.1k LOC] | 1. Written JUnit + Mockito Test Cases ~80% Packages [UkubukaReader, UkubukaWriter, UkubukaExpressionEvaluator, UkubukaExtractor, UkubukaTransformer, UkubukaLoader] 2. Was invloved in the initial design discussions with Justin for the Test Harness [Regression Suite] 3. Planned JUnit Integration Tests Lifecycle | 1. GitHub Project Setup 2. GitHub Branching Strategy 3. TravisCI Setup & Integration [Continous Integration Tool 4. CodeCov Setup & Integration [Code Coverage Tool] 5. JDK8, Eclipse, SonarQube Setup & Configuration | 1. Organized Weekly Plank Meetings 2. Organized Weekly Pair Programming Sessions 3. Using Slack to communicate with the team 4. Active participation in the project meetings & discussions
Yashvardhan Nanavati | 1. Created stories for team members for Iterations 0,1,2 2. Successfully updated status for my stories and kept track of other stories. | 1. Guided the design discussions and req analysis documents. 2. Majorly wrote the SDD document from scratch. 3. Majorly wrote the SPPP document from scratch. 4. Researched online to find the correct method to document design. | 1 | 1. Contributed in planning and writing content for iteration #0 and Iteration #1 2. Presented signigicant sections of the project in both Iteration #0 and Iteration #1. | 1. Wrote a major section of the project with complex logic. {Transformation} 2. Wrote huge classes and added scripts for API implementation [Approx 9.5k LOC] | 1. Learnt how to use Mockito + Junit 2. Wrote test cases for UkubukaBaseParser and UkubukaDFileParser 3. Assisted in JUnit Integration Tests Lifecycle planning | 1. Setup the GitHub branching strategy and documented it for other team members. 2. Explained Git Workflow to all team members and helped them setup their repos. 3. Conducted Code reviews for almost 80% of the Pull requests. | 1. Co-ordinated with team members to conduct daily and weekly team meets. 2. Guided few weekly team meetings. 3. Was the time keeper for a few team meetings. 4. Actively participated in all the team meetings and project discussions. 5. Used whatsapp and Slack for communi- -cation 6. Actively helped team members in code pair meetings.
Wenjun Shen | Finished assigned tasks on Pivotal tracker | 1. documented coding and documentation standards. 3. documented defect sofware management plan. | 1. write up test documentation | 1. Helped creating PPT on #1 and #2 iteration. | 1. Implemented csv, json, and xml comparator. | 1. Tested sytem on transfoming csv, json and xml files using Ukubuka Schema | 1. upload files comparators to Github. | 1. Asked teammates to make sure I did the implement properly.
Anirvan Maiti | Completed assigned tasks on the pivotal tracker. Reviewed the comments and made appropriate changes | 1. Contributed in design discussion 2. Contributed in building the presentations 3. Proofread all the documents |  | 1. Contributed in creating the powerpoint presentaions for the iterations. 2. Went over the presentation with the teammates before the actual presentation 3. Helped in making the powerpoint presentaions more appealing 4. Discussed with the teammates about the topic divisions for the presentation | 1. Implemented and designed prototypes of the visualizations to be added into the project | 1. Created dummy datasets for testting the prototype implemented by me 2. tested different visualizations for the same dataset and vice versa. And compared the results with kibana | 1. commited to github 2. Multiple echart visualization implementations 3. configured the echart visualization codes as per the requirements of the project | 1. Arranged pair programming sessions with teammates 2. Contributed in the design and implemetation ideas 3. Actively participated in the team meetings and team discussions 4. Used whatsapp and slack for communication with the teammates 5. Coordinated with the team leaders 6. Discussed with the teammates about implementations of extra features
Tianqi Xu | Finishing assigned story in icebox | 1. Finished most meeting minutes reports 2. Mainly finished 2nd iteration's powerpoint |  | Planned and created iteration #2's presentation and presented main functionality visualization | Designed prototype visualization implementation in js and json reader. | Designed the input dataset of json format that that can manifest the functional improvement compare to Kibana | Commited to github; implemented Echart library and it's environment | 1. Arranged meetings of iteration2 for the presentation; 2. Kept track and not of every group meeting
Aswin Vasudewan | Completed User stories in pivotal tracker. Worked on all the review comments and they were accepted. | 1. Contributed to Design discussions. 2. Invovled in Design documentation. 3. Designed XML parser. | 1. Completed Unit test , Acceptance test and test metric in TDD. 2. Updated the testcases with key test cases. | Planned and created the presentation slides along with the team member in the iteration. | 1. Implemented XML Parser in Ukubuka engine and commited the changes to Github. 2. Addressed the review comments by PM. 3. Made 3 commits with LOC 267 4. Code coverage of 78% | 1. Added the Junit and Mockito test cases for the Ukubuka XML parser. 2. Manual testing for user and buisness acceptance and performed Beta testing. | 1. Configured the Schema to accept XML based conditions. 2. Added the test xml file with the configuration. 3. Committed and added comment in github ukubuka page. | 1.Contributed in pair programming sessions 2. Contributed design and project ideas. 3. Used slack and email to communciation. 4. Attended project meetings.

## Rohit Agrawal
Week # (From Date - End Date) | Total Actual Time (This Week Tasks) (# Hours) | Total Individual Work Time (# Hours) | Total Meeting Time (# Hours) | Task Breakdown 0 - Learning 1 - Requirement Analysis 2 - Design 3 - Implementation 4 - Test 5 - Communication/Management 6 - Unclassified | Task #0 Time (# Hours) | Task #1 Time (# Hours) | Task #2 Time (# Hours) | Task #3 Time (# Hours) | Task #4 Time (# Hours) | Task #5 Time (# Hours) | Task #6 Time (# Hours) | Estimated Tasks (Next Week) | Total Estimated Time (# Hours)
09/06/2017 - 09/12/2017 | 7 | 5 | 2 | 5 - Brainstorm potential project ideas with the group. 5 - Find out the strengths of each of the group members and decide a technology stack. 5 - Brainstorm the project and team name. 5 - Mutually decide a convinient meeting time. 0 - Read more about Spring and microservices. | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 0, 1, 2, 3, 5 | 15
09/13/2017 - 09/19/2017 | 20 | 15 | 5 | 1 - Perform Requirement Analysis to understand the scope of the project and the essential features. 1 - Write a project description outline with the desirable features. 5 - Setup two different Slack channels for the general communications and the project progress updates. 5 - Setup GitHub repository and allocate roles by identifying the access levels for individual group members. 3 - Add a simple Readme file consisting of the project outline and desirable features to demonstrate GIT best practices like Branching Techniques, Commit/Squash Practices, Code Reviews, PR Merges etc. 5 - Discuss an agile methodology flavor Vanilla/Kanban and setup the JIRA Board [Taiga]. 5 - Identify and assign the various leadership roles to the group individuals in Taiga Board. 2 - Document the software installation guide for the complete technology stack including the static analysis tool and the continuous integration tool. 0 - Read about SpringBoot and the various dependency and build manager tools. | 2 | 3 | 2 | 1 | 0 | 7 | 0 | 0, 1, 2, 3, 4, 5 | 20
09/20/2017 - 09/27/2017 | 25 | 20 | 5 | 1 - Brainstormed detailed requirements and outline of the project with all the team members. 0 - Installed TeamCity, SonarQube, JDK 8, Eclipse & Plugins to setup Development Environment. 0 - Looked into the Chart Libraries like ECharts, C3, D3, NVD3, TauCharts. 0 - Read more about SOA, Microservices, Spring & SpringBoot. 0 - Looked into 3D Visualization Tools like DEX. 3 - Created PivotalTracker account and wrote UserStories along with Yash. 1,2 - Worked on main areas of SPPP along with Yash. 5 - Worked on the overall project architecture design. 5 - Documented GIT Branching strategy in detail with the branch prefixes and code reviews policies. 5 - Documented Definition of Done (DoD). 5 - Documneted Sprint lengths, story points, planning & scrum meeting times. 5 - Made smaller teams for iteration 0 and iteration 1 presentations with mutual consensus. 5 - Assigned stories and individual tasks for each team member for the upcoming sprint. 5 - Discussed the code review process with the Implementation Leader. | 4 | 2 | 3 | 2 | 0 | 9 | 0 | 0, 1, 2, 3, 4, 5 | 20
09/28/2017 - 10/04/2017 | 35 | 30 | 5 | 0 - Read Documents on Nashorn Engine. 2 - Complete Initial Skeletop & UIE Schema Design. 3 - Implemented UIE Schema Reading & Parsing. 3 - Implemented Extract, Transform & Load Workflows. 3 - Implemented Expression Evaluator. 4 - Written JUnit Test Cases For Workflows, Launcher & Evaluator. 3 - Guided Team During Pair Programming Sessions. 2 - Created Stories For Implementation Phase#1 & Test Harness Development. 3 - Actively Pushed Code On GITHub Project Repository. 5 - Conducted Plank Meetings For Sprint #1. | 4 | 2 | 3 | 15 | 5 | 6 | 0 | 0, 1, 2, 3, 4, 5 | 20
10/05/2017 - 10/11/2017 | 35 | 30 | 5 | 0 - Researched on the approach for embedding different libraries and creating visualizations in Ukubuka. 0 - Read ECharts, C3, D3 & TauCharts documentation to see how they can be embedded with Ukubuka Engine. 3 - Wrote User Stories for the next set of tasks. 2 - Designed Visualization Workflows. 3 - Completed Pair Programming sessions. 4 - Implemented Mockito Test Cases. 3 - Created Class Diagram. 5 - Conducted Weekly Plank Meetings. | 3 | 0 | 3 | 14 | 6 | 9 | 0 | 0, 1, 2, 3, 4, 5 | 25
10/12/2017 - 10/18/2017 | 30 | 25 | 5 | 0 - SOA & RESTful APIs for Ukubuka 0 - SOAP UI POST & GET Request Response 1 - Iteration #2 Detailed Requirement Analysis 3 - Created User Stories for Iteration #2 in Pivotal Tracker 3 - Discussed with Yash on the main points to be included in the SDD Document 3 - Discussed with Yash on the design patterns etc. to be used 2 - Prioritized Visualization Stories for Iteration #2 5 - Created the presentation for Iteration #1 4 - Implemented JUnit Test Cases using Mockito 3 - Code Review Tasks on GitHub 3 - Created an initial Class Diagram 5 - Created New Release Barnch for Iteration #1 Release 5 - Organized Weekly Pair Programming & Plank Meeting Sessions | 2 | 3 | 3 | 8 | 5 | 9 | 0 | 0, 1, 2, 3, 4, 5 | 25
10/19/2017-10/25/2017 | 25 | 20 | 5 | 0 - Design Patterns 1 - Iteration #2 Detailed Requirement Analysis 3 - Created User Stories for Iteration #2 3 - Discussed with Rohit on the design patterns etc. to be used 2 - Wrappers Pipeline Discussions 5 - Slack Communications 5 - Created Presentation For Iteration #1 4 - Written JUnit + Mockito Test Cases 3 - GitHub Code Reviews 5 - Team Meetings, Pair Programming Sessions 5 - Mentoring | 3 | 2 | 3 | 7 | 4 | 5 | 0 | 0, 1, 2, 3, 4, 5 | 25
10/26/2017-11/01/2017 | 25 | 20 | 5 | 0 - Aggregation Operations 0 - Relevant Datasets Research 2 - Architecture Diagram 2 - Implementation Pipelines 1 - Iteration #3 Preliminary Requirement Analysis 3 - Created User Stories 5 - Slack Communicaitions 4 - Written JUnit + Mockito Test Cases 3 - GitHub Code Reviews 5 - Team Meetings, Pair Programming Sessions 5 - Mentoring | 2 | 4 | 5 | 6 | 3 | 5 | 0 | 0, 1, 2, 3, 4, 5 | 25
11/02/2017-11/08/2017 | 15 | 10 | 5 | 0 - Datasets Research 1 - Iteration #3 Preliminary Requirement Analysis 2 - SDD Refinement 3 - Created User Stories 3 - GitHub Code Reviews 4 - Written JUnit + Mockito Test Cases 5 - Slack Communicaitions 5 - Team Meetings, Pair Programming Sessions 5 - Mentoring | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0, 1, 2, 3, 4, 5 | 25
11/09/2017-11/15/2017 | 25 | 20 | 5 | 0 - Datasets Research 0 - Graph, Bar Charts For Researched Datasets 1 - Iteration #3 Detailed Requirement Analysis 2 - SDD Refinement 2 - Sequence Diagram, Use Case Diagram 3 - Created User Stories 3 - GitHub Code Reviews 4 - Written JUnit + Mockito Test Cases 5 - Slack Communicaitions 5 - Team Meetings, Pair Programming Sessions 5 - Team Mentoring | 4 | 3 | 4 | 7 | 1 | 1 | 0 | 0, 1, 2, 3, 4, 5 | 25
11/16/2017-11/22/2017 | 25 | 20 | 5 | 0 - Datasets Research 1 - Iteration #3 Detailed Requirements Analysis 2 - SDD Refinement 3 - Created User Stories 3 - GitHub Code Reviews 3 - Visualization Implementation 3 - Aggregation Functions Implementation 4 - Written JUnit + Mockito Test Cases 5 - Slack Communicaitions 5 - Team Meetings, Pair Programming Sessions 5 - Mentoring | 2 | 4 | 3 | 6 | 1 | 4 | 0 | 0, 1, 2, 3, 4, 5 | 25
11/30/2017-12/06/2017 | 25 | 20 | 5 | 0 - Datasets Search 3 - CHarting Lubrary Implementation 4 - Written JUnit + Mockito Test Cases 5 - Team Meetings, Pair Programming Sessions 5 - Presentation Review 5 - Project Reporting 5 - Writing Meeting Minutes | 3 | 0 | 2 | 5 | 5 | 5 | 0 | 0, 1, 2, 3, 4, 5 | 25
12/07/2017-12/13/2017 | 25 | 20 | 5 | 0 - Dataset Search & Review 2 - SPPP refinement 3 - Updating Pivotal Tracker 3 - Final Presentation 4 - TDD Review 4 - Test Case Reviews 5 - Team Meetings, Pair Programming Sessions 5 - Project Reporting | 3 | 0 | 3 | 7 | 5 | 7 | 0 | 0, 1, 2, 3, 4, 5 | 25

## Yashvardhan Nanavati
Week # (From Date - End Date) | Total Actual Time (This Week Tasks) (# Hours) | Total Individual Work Time (# Hours) | Total Meeting Time (# Hours) | Task Breakdown 0 - Learning 1 - Requirement Analysis 2 - Design 3 - Implementation 4 - Test 5 - Communication/Management 6 - Unclassified | Task #0 Time (# Hours) | Task #1 Time (# Hours) | Task #2 Time (# Hours) | Task #3 Time (# Hours) | Task #4 Time (# Hours) | Task #5 Time (# Hours) | Task #6 Time (# Hours) | Estimated Tasks (Next Week) | Total Estimated Time (# Hours)
09/06/2017 - 09/12/2017 | 8 | 6 | 2 | 0 - Getting a background about the services to be implemented 5 - Assist the team leader to decide on the technologies to be used and assign work to the respective leaders 5 - Coordinate with the team leader and members to setup a weekly meeting schedule 5 - Make a document for the steps to be followed while working with git on the project 5 - Discuss more about the specifics of the project and find a project name | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0, 1, 2, 3, 5 | 15
09/13/2017 - 09/19/2017 | 18 | 13 | 5 | 0 - Getting acquainted with the Taiga Board. 0 - Digging deeper into Kibana which is similar to our idea with lesser features. 1 - Participate in the requirement analysis of the project. 2 - Review the software installation guide for the complete technology stack. 2 - Figure out shortcomings of Kibana and research on the methods using which we can avoid those in our app. 5 - Discuss agile methodologies such as Vanilla/Kanban and help Rohit in setting up the JIRA Board [Taiga]. 5 - Coordinate with team members to assure that the work is on track. 5 - Review work of other team members and report to the team leader. | 4 | 3 | 4 | 0 | 0 | 6 | 0 | 0, 1, 2, 3, 4, 5 | 18
09/20/2017 - 09/27/2017 | 20 | 15 | 5 | 0 - Found and researched on an open-source project named DEX which inhibits 3D visualizations 0 - Learnt more about Spring and SpringBoot. 0 - Getting acquainted with Spring environment 0 - Setup the development environment 1 - Brainstormed requirements and outline of the project with all the team members 1,2 - Documented huge chunks of SPPP 3 - Setup the pivotal tracker and made user story cards with Rohit 5 - Conveyed the plan to all team members 5 - Co-ordinated with all the team members to setup an extra meeting for this week to finish up the requirements of iteration 0 5 - Made teams for presenting iteration 0 and iteration 1 with mutual consensus 5 - Discussed individual work for each team member and story points per sprint for them 5 - Discussed branching and configuration nuances such as hotfixes/features/bugs with the team 5 - Discussed the development model and project schedule with team leader | 4 | 2 | 3 | 2 | 0 | 8 | 0 | 0,1,2,3,4,5 | 20
09/28/2017 - 10/04/2017 | 35 | 30 | 5 | 0 - Researched about Nashorn Engine for integrating visualization 0 - Learned more nuances about Spring, Mockito, SonarQube 2 - Designed workflows for Extract, Transform and Load 2 - Designed implementation methods with Rohit 3 - Helped team members to set up the configuration in Eclipse 3 - Guided team members in the git workflow and directly importing git projects in Eclipse 3 - Assisted Rohit in implementing ETL processes for Ukubuka 3 - Implemented Transform class for carrying out the transformation logic 3 - Did multiple code reviews on Github and made suggested minor changes 4 - Learnt to write test cases using JUnit 5 - Co-rdinated with team members to follow-up on their tasks 5 - Weekly plank meetings 5 - Reported to Rohit regarding the progress and discussed future meeting plans | 5 | 0 | 5 | 12 | 4 | 9 | 0 | 0,1,2,3,4,5 | 20
10/05/2017 - 10/11/2017 | 25 | 20 | 5 | 0 - Researched about creating class diagram for the project 3 - Created user stories for other team members 0 - Researched about ECharts and Tau-charts to integrate them with our engine 2 - Designed workflows for Visualization using API's 2 - Designed visualization implementation methods with Rohit 3 - Guided the team meeting 4 - Implementing test cases using Mockito 3 - Did multiple code reviews on Github and made suggested minor changes 3 - Created class diagram for the project 4 - Learnt to write test cases using JUnit 5 - Co-rdinated with team members to follow-up on their tasks 5 - Weekly plank meetings 5 - Reported to Rohit regarding the progress and discussed future meeting plans | 3 | 0 | 3 | 8 | 2 | 9 | 0 | 0,1,2,3,4,5 | 20
10/12/2017 - 10/18/2017 | 25 | 20 | 5 | 0 - Researched about creating architecture diagram for the project 3 - Created user stories for other team members 1 - Analyzed requirements and targets for Iteration #1 release 3 - Created the SDD document for Iteration #1 3 - Updated SPPP to include burndown chart 0 - Researched on using Java to connect API's 2 - Planned visualization implementation methods with Rohit 5 - Communicated the first release of project in the team meeting 4 - Implementing test cases using Mockito 3 - Did multiple code reviews on Github and made suggested minor changes 3 - Updated class diagram for the project with recent changes 5 - Co-rdinated with team members to follow-up on their tasks 5 - Weekly plank meetings 5 - Reported to Rohit regarding the progress and discussed future meeting plans | 2 | 1 | 1 | 10 | 2 | 9 | 0 | 0,1,2,3,4,5 | 20
10/19/2017-10/25/2017 | 30 | 25 | 5 | 0 - Python Wrapper for Ukubuka 1 - Iteration #2 Detailed Requirement Analysis 3 - Created User Stories for Iteration #2 3 - Authored the SDD Document from scratch. 3 - Discussed with Rohit on the design patterns etc. to be used 2 - Discussed scope of Iteration #2 with Rohit 5 - Assigned work to team members other than rohit to encourage them to write code 5 - Followed up on Slack regarding progress of this sprint 5 - Contributed in the presentation for Iteration #1 5 - Briefed team members regarding their presentation part in Iteration #1 presentation 4 - Implemented JUnit Test Cases using Mockito 3 - Code Reviews on GitHub 5 - Lead the team meeting and the code pair meetings 5 - Briefed team members regarding their work in Iteration #2 and solved ther doubts regarding the same. | 3 | 2 | 3 | 10 | 4 | 8 | 0 | 0,1,2,3,4,5 | 20
10/26/2017-11/1/2017 | 25 | 20 | 5 | 0 - Learnt anout Design Patterns 1 - Iteration #2 Detailed Requirement Analysis and retro 3 - Discussed with Rohit on the design patterns etc. to be used 2 - Python Wrappers Discussion 3 - wrote meeting minutes 3 - Created User Stories for Iteration #2 5 - Slack & whatsapp Co-ordination 5 - Created Documentation and SDD for Iteration #1 4 - Wrote JUnit Test Cases 3 - GitHub Code Reviews 5 - Team Meetings, Pair Programming Sessions 5 - Helped team members with their work 5 - Followed up with work of team members | 2 | 3 | 3 | 7 | 3 | 7 | 0 | 0,1,2,3,4,5 | 20
11/2/2017-11/8/2017 | 25 | 20 | 5 | 4 - Wrote JUnit Test Cases for Ukubuka Parser class 3 - GitHub Code Reviews for team members 5 - Team Meetings, Pair Programming Sessions 5 - Helped team members with their work 5 - Followed up with work of team members 3 - Added Software Architecture Diagram and Description to SDD 3 - Helped team members wit their work 2 - Designing a simple UI for demo in Iteration #3 3 - Final refining of SDD 0 - Learnt about how to solve CORS 5 - Slack & whatsapp Co-ordination 1 - Iteration #2 review and feedback | 2 | 2 | 4 | 6 | 4 | 8 | 0 | 0,1,2,3,4,5 | 20
11/9/2017-11/16/2017 | 20 | 15 | 5 | 0 - Datasets Finding 0 - Graph, Bar Charts implementation with Rohit 1 - Iteration #3 Requirement Analysis 2 - SDD Refinement 2 - Sequence Diagram, Use Case Diagram 3 - Created User Stories 3 - GitHub Code Reviews 4 - Written JUnit + Mockito Test Cases 5 - Team Meetings, Pair Programming Sessions 5 - Guiding the team 5 - Reporting work to Rohit | 2 | 3 | 2 | 1 | 3 | 4 | 0 | 0,1,2,3,4,5 | 20
11/16/2017-11/29/2017 | 30 | 25 | 5 | 0 - Datasets Finding 0 - Python wrapper for Ukubuka 1 - Iteration #3 Requirement Analysis 2 - SDD Refinement 3 - Created User Stories 3 - GitHub Code Reviews 3 - Implementation of Charts with Rohit 4 - Written JUnit + Mockito Test Cases 5 - Team Meetings, Pair Programming Sessions 5 - Guiding the team 5 - Reporting work to Rohit | 3 | 2 | 3 | 7 | 6 | 9 | 0 | 0,1,2,3,4,5 | 30
11/30/2017-12/06/2017 | 20 | 15 | 5 | 0 - Datasets Finding 3 - Implementation of Charts with Rohit 4 - Written JUnit + Mockito Test Cases 5 - Team Meetings, Pair Programming Sessions 5 - Guiding the team 5 - Reporting work to Rohit 5 - Writing Meeting minutes | 3 | 0 | 2 | 3 | 2 | 5 | 0 | 0,1,2,3,4,5 | 20
12/07/2017-12/13/2017 | 25 | 20 | 5 | 0- Dataset finding 2 - SDD Refinement 2 - SPPP refinement 3 - Updating Pivotal Tracker 3 - Making Presentation for Final Presentation 4 - TDD Review 4 - Reviewing Test cases and structure 5 - Team Meetings, Pair Programming Sessions 5 - Guiding the team 5 - Reporting work to Rohit | 3 | 0 | 3 | 7 | 5 | 7 | 0 | 0,1,2,3,4,5 | 25

## Anirvan Maiti
Week # (From Date - End Date) | Total Actual Time (This Week Tasks) (# Hours) | Total Individual Work Time (# Hours) | Total Meeting Time (# Hours) | Task Breakdown 0 - Learning 1 - Requirement Analysis 2 - Design 3 - Implementation 4 - Test 5 - Communication/Management 6 - Unclassified | Task #0 Time (# Hours) | Task #1 Time (# Hours) | Task #2 Time (# Hours) | Task #3 Time (# Hours) | Task #4 Time (# Hours) | Task #5 Time (# Hours) | Task #6 Time (# Hours) | Estimated Tasks (Next Week) | Total Estimated Time (# Hours)
09/06/2017 - 09/12/2017 | 10 | 8 | 2 | 5 - discussed the project ideas of the group 5 - discussed the pros and cons of each member sproject idea 5 - decided the team name 5 - decided a common meeting time and place as per every members convenience 0 - read more about the project and its use cases | 3 |  |  |  |  | 5 |  | 0, 1, 2, 3, 5 | 15
09/13/2017 - 09/19/2017 | 22 | 17 | 5 | 0 - researched about kibana. Its abilities and short comings 1 - discussed the scope of the projects and how to over come the short comings of kibana with the team 3 - set up the environment which will be used by all the members of the team during the entire duration of the project 5 - documented the software installation links and installation steps for the team members 0 - learnt more about agile methodology so that we can implement in the development process 0 - Read about Taiga board and how it works 5 - discussed the workflow skeleton for the project with all the team members 0 - researched about the testing process for the project and analyzed them 5 - discussed with the team about the requirements of the software and the fetures which can be added in it 0 - reviewed and read about the softwares and platforms to be used for the project | 5 | 2 | 2 | 1 | 0 | 7 |  | 0, 1, 2, 3, 4, 5 | 20
09/20/2017 - 09/27/2017 | 20 | 15 | 5 | 0 - researched and read more about the DEX visualization tool 0 - set up the environment along with the additional packages 0,1 - documented the SPPP along with other team members 5 - prepared for the iteration 0 presentation along with the team members 2 - Edited the iteration 0 presentation PPT 5 - mutually created smaller teams for alternate iteration presentations 1 - discussed the requirements of the project with the team members 5 - mutually discussed the strengths and weaknesses of the team members 0 - learnt and researched about other visualizations techniques 0 - learnt about the various testing processes which will/can be implemented in the project | 4 | 2 | 1 | 0 | 0 | 8 | 0 | 0,1,2,3,4,5 | 20
09/28/2017 - 10/04/2017 | 21 | 16 | 5 | 0 - read and discussed the user stories and requirement analysis 5 - attended team meeting to discuss the role of every member for iteration 1 0 - learnt the git workflow 3 - setup the environment in eclipse 0 - learnt how the pivortal tracker works 0, 1 - read E3 and Tau chart documentation and understood its implementation in the project 5 - discussed with Yash about the ETL process for Ukubuka 3 - implemented E3 charts on local machine with a dummy dataset 5 - Discussed with Aswin about the Parser implementation | 4 | 2 | 0 | 4 | 0 | 6 | 0 | 0, 1, 2, 3, 4, 5 | 20
10/05/2017 - 10/11/2017 | 27 | 22 | 5 | 0 - read the class notes and PowerPoint presentations to learn class diagram 5, 1 - discussed the scope and implemetation of the Transform class with Yash 0, 5 - read the documentation of Jackson and discussed about its implementation with Aswin 5, 1 - Discussed about the workflow of ukubuka engine with Rohit 0, 2, 3 - executed different types of visualization on my local machine and learn their usabilities 0 - learnt test harness from class notes and PowerPoint presentations 4 - tested different visualization techniques | 6 | 2 | 2 | 2 | 2 | 8 | 0 | 0, 1, 2, 3, 4, 5 | 20
10/12/2017 - 10/18/2017 | 31 | 26 | 5 | 0 - Learnt the Transform class 3 - collected different graph datsets and created smaller chunks of them for testing of the transform stage 5, 1 - Discussed with Rohit the different Transformation tasks being performed in the Ukubuka engine 3 - executed python script to perform different tasks on the chunks of datasets like changing of delimiters, changing the header name, swapping of columns, normalization of a column, etc. 3 - repeated the above tasks on 5 more datasets and learnt the scope of trsnsformations with different types of datasets 5, 2 - discussed the presentaion slides for the Iteration 1 with all the teammates 4 - tested the chunks of the datasets on the ukubuka engine 5 - discussed scope visualization for the next iteration | 2 | 2 | 2 | 8 | 4 | 8 | 0 | 0, 1, 2, 3, 4, 5 | 20
10/19/2017 - 10/25/2017 | 35 | 30 | 5 | 0 - Studied the visualization implementation in DEX 5 - Discussed the implementation of ECharts and Tau charts with Tianqi 0 - Learnt the Echarts usability and implementation 3 - Designed the html page and implemented the echart packages to implement the graphs on the local machine 0 - learnt about javascript usage and integration with html files 5 - discussed the html and javascript implementation with Tianqi | 6 | 0 | 0 | 12 | 0 | 12 | 0 | 0,1,2,3,4,5 | 20
10/26/2017 - 11/01/2017 | 35 | 30 | 5 | 5 - Pair programming session with Tianqi 5 - Discussed the javascript implementation and data extraction with Aswin and Tianqi 0 - studied graph demos in echart very closely 0 - studied the packages and the APIs used in Echarts 5 - implemented the various graph manipulations on the local machine 0 - learnt TDD, refactoring and regression testing 1 - analyzed the kind of visualization required in the project 4 - tested the graph implementations hosted locally | 6 | 2 | 0 | 0 | 4 | 18 | 0 | 0,1,2,3,4,5 | 20
11/02/2017 - 11/08/2017 | 35 | 30 | 5 | 5 - Pair programming session with Tianqi 2 - Design the dynamic data visualization in echarts 4 - tested the javascript with various json files 5 - discussed the data feeding process into the javascript with Tianqi and Aswin 5 - discussed how visualization is to be implemented into the project with the entire team 5 - Team meeting 5 - discussed the iteration 2 demo with the team 0 - learnt echarts API usage | 2 | 0 | 4 | 0 | 4 | 20 | 0 | 0,1,2,3,4,5 | 20
11/09/2017 - 11/16/2017 | 21 | 16 | 5 | 5 - discussed about type of visualizations to be added with the teammates 5 - brain stormed about visualization implementation with the teammates 5 - discussed with aswin and tianqi about html implementation 4 - tested json files on the javascript implementation 1 - reviewed HW4 and tried to analyze the requirements needed for our project 5 - pair programming session with aswin | 0 | 2 | 0 | 0 | 4 | 10 | 0 | 0,1,2,3,4,5 | 20
11/16/2017 - 11/29/2017 | 19 | 14 | 5 | 0 - learnt the functionalities and the limitations of the dex visualization tool 2 - finalizaed the visualizations that needed to be implemented in the project 2 - discussed with the teammates about how the ukubuka engine generated the visualization 2 - tweaked and tested the chartts code to understand the kind of visualization required 5 - communicated with teammates about the code connection between ETL and visualization 0 - learnt few code implementations in dex and tried implementing it | 6 | 0 | 6 | 0 | 0 | 2 | 0 | 0,1,2,3,4,5 | 30
11/30/2017 - 12/06/2017 | 16 | 11 | 5 | 0 - learnt the functionalitities of kibana and its short comings 0 - finding proper dataset 5 - team meeting 1 - checked the SDD and SPPP documents 5 - communicated with the team about the echarts code 0 - learnt the json library and its implementations | 6 | 1 | 0 | 0 | 0 | 4 | 0 | 0,1,2,3,4,5 | 20
12/07/2017 - 12/13/2017 | 20 | 15 | 5 | 0 - finding proper dataset 3 - contributed in final presentation 3 - prepared for the final presentation 5 - discussed with the teammates about the intial planned targets and the targets reached after project completion 5 - discussed the limitations and future implementations of the project | 3 | 0 | 0 | 4 | 0 | 8 | 0 | 0,1,2,3,4,5 | 25

## Tianqi Xu
Week # (From Date - End Date) | Total Actual Time (This Week Tasks) (# Hours) | Total Individual Work Time (# Hours) | Total Meeting Time (# Hours) | Task Breakdown 0 - Learning 1 - Requirement Analysis 2 - Design 3 - Implementation 4 - Test 5 - Communication/Management 6 - Unclassified | Task #0 Time (# Hours) | Task #1 Time (# Hours) | Task #2 Time (# Hours) | Task #3 Time (# Hours) | Task #4 Time (# Hours) | Task #5 Time (# Hours) | Task #6 Time (# Hours) | Estimated Tasks (Next Week) | Total Estimated Time (# Hours)
09/06/2017 - 09/12/2017 | 0 | 0 | 0 | 6 - trying to register for the class. 0 - learning course material. | - | - | - | - | - | - | - | 0, 1, 2, 5 | 15
09/13/2017 - 09/19/2017 | 15 | 10 | 5 | 0 - read the papers about agile methodologies and no-silver-bullets. 0 - written assignments. 1 - determined group name. 1 - determined that we are going to use data visualization as our project topic. 1 - determined that we will use java, javascript and possibly matlab as our main language. 2 - finished the documentation for environment installation. 5 - Assigned role and different task for each group member. 5 - set a temporary group meeting time. 5 - get enrolled into pivot and github for future work | 7 | 1 | 1 | 0 | 0 | 7 | 0 | 0,1,2,3,5 | 20
09/20/2017 - 09/27/2017 | 17 | 12 | 5 | 0 - learnt the basic functionality of kibana and it's drawbacks that we want to improve 0 - recording the meeting minutes 0 - get to know eclipses and json more 0 - Setup thte environment 1 - Brainstormed requirements and assign more detailed tasks to group member 5 - Discussed more detailed plan for our 3 iterations: iteration 1 for parsing the data; iteration 2 for visualizing the parsed data; iteration 3 for design a wonderful UI and show the visualization in the UI 5 - Setup a fixed meeting time 5 - Determine the presentation cast | 4 | 2 | 3 | 0 | 0 | 8 | 0 | 0,1,2,3,4,5 | 20
09/28/2017 - 10/04/2017 | 10 | 5 | 5 | 0 - read the user story powerpoint and requirement analysis powerpoints 0 - written assignments 1 - meeting to determine each person's assignment in iteration1 2 - determined that we will implement XML parser, CSV parser, and Delimit file parser 3 - implemented code for parsing json data into Java arrayList 5 - determined the format of the parsing data with teammates | 4 | 2 | 1 | 5 | 0 | 1 | 0 | 1,2,3,4,5,6 | 25
10/05/2017-10/11/2017 | 18 | 15 | 3 | 0 - understood the Ukubuka core flow chart 1 - modified SDD and SPPP with teammate 2 - researched about Json library available in Java 2 - designed UkubukaJsonParser class in Java; using Jackson library and another object class to store the json data in Java 3 - Implement slcass UkubukaJsonParse 5 - Communicated with the team about the code that i implemented | 3 | 2 | 3 | 5 | 0 | 5 | 0 | 1,2,3,4,5,6 | 25
10/12/2017 - 10/18/2017 | 15 | 12 | 3 | 0 - understand about our test case and PPT 0 - finishing peer review 1 - make up my own slides for iteration 1 2 - designed my parsed java object's format according to the visualization we need 3 - modified my parsing functions | 3 | 3 | 3 | 3 | 0 | 3 | 0 | 1,2,3,4,5 | 20
10/19/2017 - 10/25/2017 | 16 | 15 | 1 | 0 - learn the visualization tool Dex: their basic functionality and limitation 1 - estimate the amount of time that we need for doing the visualization 2 - Designed our pattern of visualization that we are gonna need to use 3 - went through the basic code structure of dex and made some modification 4 - tested the modification of dex. | 1 | 1 | 1 | 4 | 4 | 0 | 0 | 1,2,3,4 | 12
10/26/2017 - 11/01/2017 | 18 | 17 | 1 | 0 - learned TDD, Refactoring and regression testing and wrote homework 1 - analyze what kind of visualization do we exactly need for our project Ukubuka 2 - Designed test cases for testing our first implementation of visualization 3 - Hardcoded the tutorial level visualization with out connecting it to Ukubuka file. 4 - Test our Javacript implementation with json test files | 9 | 1 | 2 | 6 | 2 | 1 | 0 | 1,2,3,4,5 | 21
11/02/2017 - 11/08/2017 | 20 | 19 | 1 | 0 - learned Echart library and it's javascripte library 2 - determine which kinds of visualization we need finally 2 - determined how Ukubuka is connecting with the visualization code 3 - Implemented the javascript code in HTML to actually visualize the data 4 - use json test case to test the visualization code 5 - communicated with Yash and Rohit about the connection part between Visualization and data ETL 5 - communicate with Anirvan and Aswin about the code implementation | 1 | 1 | 1 | 20 | 1 | 1 | 0 | 1,2,3,4,5 | 25
11/09/2017 - 11/15/2017 | 8 | 3 | 5 | 0 - learned about Kibana 1 - Analyzed HW4 1 - analyze what kind of visualization do we exactly need for our project Ukubuka 2 - Designed test cases for testing our first implementation of visualization 3 - Hardcoded the tutorial level visualization with out connecting it to Ukubuka file. 4 - Test our Javacript implementation with json test files | 2 | 2 | 2 | 21 | 2 | 2 | 1 | 1,2,3,4,6 | 26
11/16/2017 - 11/22/2017 | 10 | 5 | 5 | 0 - learned Echart library and it's javascripte library 2 - determine which kinds of visualization we need finally 2 - determined how Ukubuka is connecting with the visualization code 3 - Implemented the javascript code in HTML to actually visualize the data 4 - use json test case to test the visualization code 5 - communicated with Yash and Rohit about the connection part between Visualization and data ETL 5 - communicate with Anirvan and Aswin about the code implementation | 2 | 2 | 2 | 21 | 2 | 3 | 2 | 1,2,3,4,7 | 27
11/16/2017 - 11/29/2017 | 15 | 10 | 5 | 0 - learn the visualization tool Dex: their basic functionality and limitation 1 - estimate the amount of time that we need for doing the visualization 2 - Designed our pattern of visualization that we are gonna need to use 3 - went through the basic code structure of dex and made some modification 4 - tested the modification of dex. | 3 | 3 | 3 | 22 | 3 | 4 | 3 | 1,2,3,4,8 | 28
11/30/2017 - 12/06/2017 | 12 | 9 | 3 | 0 - understood the Ukubuka core flow chart 1 - modified SDD and SPPP with teammate 2 - researched about Json library available in Java 2 - designed UkubukaJsonParser class in Java; using Jackson library and another object class to store the json data in Java 3 - Implement slcass UkubukaJsonParse 5 - Communicated with the team about the code that i implemented | 3 | 3 | 3 | 22 | 3 | 5 | 4 | 1,2,3,4,9 | 29
12/07/2017 - 12/13/2017 | 13 | 3 | 10 | 4 - Prepared Final test case and implemented to Ukubuka 3 - Wrote slides for presentation 3 - Prepared presentation 6 - Went through presentation with teammate 6 - Bought starbucks to warm up for presentation 6 - Surfing on facebook and youtube to chill for presentation | 4 | 4 | 4 | 23 | 4 | 6 | 5 | 1,2,3,4,10 | 30

## Wenjun Shen
Week # (From Date - End Date) | Total Actual Time (This Week Tasks) (# Hours) | Total Individual Work Time (# Hours) | Total Meeting Time (# Hours) | Task Breakdown 0 - Learning 1 - Requirement Analysis 2 - Design 3 - Implementation 4 - Test 5 - Communication/Management 6 - Unclassified | Task #0 Time (# Hours) | Task #1 Time (# Hours) | Task #2 Time (# Hours) | Task #3 Time (# Hours) | Task #4 Time (# Hours) | Task #5 Time (# Hours) | Task #6 Time (# Hours) | Estimated Tasks (Next Week) | Total Estimated Time (# Hours)
09/06/2017 - 09/12/2017 | 5 | 3 | 2 | 0- Learn agile development. 0- Learn scrum master. 0-Learn development process. 5- Dicuss potenial project ideas. 5-Dicuss poteintial use of technologies. | 3 | 0 | 0 | 0 | 0 | 2 | 0 | 0,1,5 | 10
09/13/2017 - 09/19/2017 | 11 | 6 | 5 | 0- Learn Taiga.io. 0- Learn Sprint. 0- Learn more about agile. 1-install eclipse and other dependencies. 1-document enviornment requirement. 5- set up github repo. 5- determine teamleader roles. 5- determine use java as programming language. | 2 | 4 | 0 | 0 | 0 | 5 | 0 | 0, 1, 2, 5 | 10
09/20/2017 - 09/27/2017 | 15 | 10 | 5 | 0-Learn Kibana. 0-Learn Spring. 2-design iteration 0 presentation. 5-create project on pivotal tracker. 5-document coding standards. 5-document documentation standards. 5-document defect sofware management plan. 5-assign tech tasks for iteration 1. | 4 | 0 | 3 | 0 | 0 | 5 | 0 | 0, 1, 2, 3, 4, 5 | 10
09/28/2017 - 10/4/2017 | 10 | 9 | 1 | 0-Learn Jackson package. 0-Learn install maven in eclipse. 0-Learn open github repo via eclipse. 0-Learn Ukubuka Schema. 3-Implement csv to json parser. 3-set up pom.xml 5-Communicate with teammates on use what side packages to implement parser | 4 | 0 | 5 | 0 | 0 | 1 | 0 | 0, 1, 2, 3, 4, 5 | 15
10/05/2017 - 10/11/2017 | 15 | 10 | 5 | 0-Learn Test Harness. 0-Learn class diagram. 1-Anlysis what kind of tests will need to test Ukubuka engine. 2- use packeage to automatically generate class digram in eclispe. 2-Design Test Harness. 3-deliver user sotry 5-Pick up tasks from the pivitoal tracker 5-Update projects from github 5-Communicate with Yash on the ideas of implementing test framework | 5 | 2 | 2 | 1 | 0 | 5 | 0 | 1, 2, 3, 4, 5 | 15
10/12/2017 - 10/18/2017 | 15 | 10 | 5 | 2-Design Test Harness. 3-Create Ukubuka Schema. 3-Implement python scrpit to perform transformantions(split files, add column, remove column, csv to semi column separated). 3-Implement separate application to test Ukubuka. 4-Test simple partioton and merge transformation. 5-Discuss implementation of testing application with teammates. 5-Report potential bugs 6-Desgin ppt for test harness in iteration 1. 6-Collect data from Echart. | 0 | 0 | 2 | 10 | 1 | 1 | 1 | 0, 1, 2, 3, 4, 5 | 15
10/19/2017 - 10/25/2017 | 11 | 6 | 5 | 0-Learn Maven project XMLunit. 0-Learn Maven project JSONCompare. 1-Analyze comparator requirement. 3-Imlement compareCSV class. 3-Implement compareJSON class. 3-Implement compareXML class. | 4 | 1 | 0 | 1 | 0 | 0 | 0 | 3 | 10
10/26/2017 - 11/01/2017 | 14 | 9 | 5 | 0-learn push local eclipse project to github 3-Implement test launcher class. 3-Imlement compareCSV class. 3-Implement compareJSON class. 3-Implement compareXML class. | 1 | 0 | 0 | 8 | 0 | 0 | 0 | 3,5 | 10
11/02/2017 - 11/08/2017 | 15 | 10 | 5 | 3-Imlement compareCSV class. 3-Implement compareJSON class. 3-Implement compareXML class. 3-split data use python script. 3-use Ukubuka to obtain the output file. 3-create testcases to test comparator. 5-disccus and prepare presentation | 0 | 0 | 8 | 0 | 2 | 0 | 0 | 3 | 10
11/09/2017 - 11/15/2017 | 15 | 10 | 5 | 3-Implement compareJSON class. 3-Implement compareXML class. 3-split data use python script. 3-use Ukubuka to obtain the output file. 3-create testcases to test comparator. 5-disccus and prepare presentation | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 3 | 10
11/16/2017 - 11/22/2017 | 15 | 10 | 5 | 4- create csv test cases 4- create json test cases 4- create xml test cases 6-Testing Documentation | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 4 | 5
11/30/2017 - 12//06/2017 | 10 | 5 | 5 | 4- create csv test cases 4- create json test cases 4- create xml test cases 6-Testing Documentation | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 4 | 5
12/07/2017 - 12/23/2017 | 10 | 5 | 5 | 4- create csv test cases 4- create json test cases 4- create xml test cases 6-Testing Documentation | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 4 | 5

## Aswin V.
Week # (From Date - End Date) | Total Actual Time (This Week Tasks) (# Hours) | Total Individual Work Time (# Hours) | Total Meeting Time (# Hours) | Task Breakdown 0 - Learning 1 - Requirement Analysis 2 - Design 3 - Implementation 4 - Test 5 - Communication/Management 6 - Unclassified | Task #0 Time (# Hours) | Task #1 Time (# Hours) | Task #2 Time (# Hours) | Task #3 Time (# Hours) | Task #4 Time (# Hours) | Task #5 Time (# Hours) | Task #6 Time (# Hours) | Estimated Tasks (Next Week) | Total Estimated Time (# Hours)
09/06/2017 - 09/12/2017 | 10 | 8 | 2 | 5 - Team meeting on project ideas 5 - Identified the key roles of every individual team amte 5 - Selection on project name and overview 5 - Decided about pair programming and team meetings 0 - Preparation on the server and java design | 5 | 0 | 0 | 0 | 0 | 5 | 0 | 0, 1, 2, 3, 5 | 15
09/13/2017 - 09/19/2017 | 22 | 18 | 4 | 0 - Read about on other similar projects like kibana 1 - Analysis on kibana and the shortcomings associated with kibana 3 - Eclipse environment and JRE versions for the projects 5 - Documentation of software and other API used. 5 - The over all working skeleton of the project 0 - Learning on Testing process 5 - Discussion on features of the project 0 - Review on the platform 0 - Learning on Agile methodologies and work flow 0 - Taiga board and its working | 5 | 5 | 0 | 2 | 0 | 10 |  | 0, 1, 2, 3, 4, 5 | 22
09/20/2017 - 09/27/2017 | 20 | 15 | 5 | 0 - Research on Visualization model in ukubuka 0 - Importing the packages that are to be supported 5 - Worked on smaller teams for individual works 1 - Requirement study for the project 5 - Discussion of roles that each team mate would play in the project 0 - Learnt about working of kibana 0 - Research on testing frame works to be included 0,1 - Documentation of SPPP with team members 5 - Preparation for presentation 2 - PPT related work for the presentation and toic flow | 5 | 5 | 2 | 0 | 0 | 8 | 0 | 0,1,2,3,4,5 | 20
09/28/2017 - 10/04/2017 | 20 | 15 | 5 | 0 - Learnt about using XML Parser to accept user input XML to visualize 1 - Researched about using Jackson frame work for the parser 2 - Imported the jackson framework and made sure ukubuka design supports the changes 3 - Code changes to implement the XML parser 4 - Tested the parser in local and identified a key issue 5 - Discussed about the issue of jackson not accepting redudant XML tags 0 - Researched about the deserialization of the jackson frame work 3 - Tried implementing the private serializer but found that root node was missing 1 - Analysis on accepting the redudant tags in XML to json parsing | 3 | 4 | 3 | 5 | 2 | 3 | 0 | 0,1,2,3,4,5 | 20
10/05/2017 - 10/11/2017 | 20 | 17 | 3 | 0 - Learnt about the pitfalls of using jackson frame work 1- Analysed about using org JSON frame work to implement parser 2 - The new frame work support from the ukubuka pom 3 - Implemented the org JSON code in local to parse the XML 4 - Tested in local the working of new org json parser 5 - Communicated the problems with project manager of using jackson 0 - On combined learning we narrowed to use org JSON 4 - Tested the org.JSON results and found the need for formating the results 1- Analysed on formating the JSON results according to the ukubuka design | 4 | 3 | 3 | 5 | 3 | 2 | 0 | 0,1,2,4,5 | 20
10/12/2017 - 10/18/2017 | 20 | 15 | 5 | 0 - Learning the overall working of Extract, Transform and Load 2 - Designed the primilinary version of architecture diagram 1 - The analysis on data sets that are to be supported in ukubuka 4 - The E chart library and other visualization tools test to see the working 5 - Participated in the discussion for presentation 1 - Studied on the unit testing framework that will be extended to the XML parser 0 - Understood about the transform opeartions from the prject manager | 6 | 4 | 5 | 0 | 3 | 2 |  | 0,1,2,3,4,5 | 20
10/19/2017 - 10/25/2017 | 20 | 17 | 3 | 0 - Learnt on using XML based input to ukubuka engine. 1 - Analysed about using the XML in Schema Json input. 2 - Designed the XML parser within the Extarction process in ukubuka. 3 - Implemented the XML parser in reader to read the XML 4 - Tested the XML parsing in the base class. 5 - Communicated the XML details to the PM. | 4 | 2 | 2 | 8 | 2 | 2
10/26/2017 - 11/01/2017 | 20 | 17 | 3 | 0 - Learnt about using XML Stream reader for implementation. 1 - Analyzed the Garbage collection would be less when read as Stream. 2 - Designed the stream reader operation in the Extract phase. 3 - Implemented the XML stream reader operation. 4 - Tested the Stream input weighed it accross other parsing 5 - Finalized about using XML stream after discussion with PM. | 4 | 2 | 3 | 7 | 2 | 2
11/02/2017 - 11/08/2017 | 25 | 22 | 3 | 0 - Learnt about using Stack Data structure in parsing the parent child tags 1 - Analyzed efficient ways of finding the parent tag in the XML input file 2 - Designed the child class for stack operations in XML 3 - Implemented the parsing of child and parent tags in XML 4 - Tested the tags by providing other input XML filles in Schema 5 - Communicated the team about recent changes in team meetings | 6 | 4 | 4 | 6 | 3 | 2
11/08/2017 - 11/16/2017 | 20 | 17 | 3 | 0 - Learnt about using list of strings to push the parsed XML to the next phase 1 - Analysed about the delimiters for the file and element 2 - Designed the format of return type in XML parsing 3 - Implemented the Delimiters and formated the parsed input 4 - Tested the format by local debugging 5 - Attended team meetings to understand overall progress of the project. | 4 | 2 | 2 | 8 | 2 | 2
11/16/2017 - 11/29/2017 | 25 | 22 | 3 | 0 - Learnt about using Junit and Mockito unit testing framework 1 - Analysed the Mock and injecting mock and Assertion rules. 2 - Designed the unit test for the XML based visualization 3 - Implemented the unit test cases in Junit and Mockito 4 - Followed TDD and tested that all test cases are passing 5 - Co ordinated with the team for presentation | 5 | 2 | 3 | 10 | 3 | 2
11/30/2017 - 12/06/2017 | 20 | 17 | 3 | 0 - Learnt about Deployment and Code coverage 1 - Analyzed to improve the code coverage for XML parser 2 - Design level over view of merging with master branch 3 - Deployed the code and addressed the review comments. 4- Tested if git build is passing and made sure code coverage is met. 5 - Discussed about the build details with Yash for improving code coverage | 5 | 3 | 2 | 7 | 2 | 1
12/07/2017 - 12/13/2017 | 20 | 17 | 3 | 0 - Learnt about documentation standards for the TDD document. 1 - Analysed all the testing pahses that were used in past. 2 - Designed the document to cover key test methods used, 3 - Implemented the updates in document. 4 - Checked with Yash that the changes comply with ukubuka 5 - Communicated about the test cases that were updated. | 2 | 3 | 3 | 10 | 1 | 1